## How to use
WeQuote CRM — Phase 1 QA checklist
Source | Derived from WeQuote-CRM-Phase-1-PRD.html — acceptance criteria (§B3), requirements (§B2) and the delivery gate (§A14).
Sheets | Summary · Delivery gate · Phase 1A / 1B / 1C · Recipe coverage · Regression
Fill in | Status onwards. Everything left of Status describes the test and should not be edited.
Status values | Not run · Pass · Fail · Blocked · N/A
What blocks a release | Fail, Blocked and Not run block. Pass and N/A do not.
Using N/A | Only for a test that cannot apply to this release. It must carry a reason in Notes and a name in 'Waiver approved by'. The Summary counts unapproved N/A separately.
Applies from | On Regression, the earliest release a rule can be tested in. A Phase 1A gate only counts rules that apply from Phase 1A.
Method | Manual, Automated or Both. The PRD requires the resolver, tenancy and duplicate tests to be automated — record the CI link under Evidence.
Priority | P1 must pass before the release ships. P2 needs a named owner to accept any exception. P3 is optional.
Date format | YYYY-MM-DD
Example row | Status: Fail · Actual result: Deal stayed in Qualified · Build: 1A-rc3 · Environment: Staging · Browser: Chrome 141 / macOS · Test data: D-0348 · Evidence: jira/WQ-1183 · Defect ID: WQ-1183 · Tester: KW · Date: 2026-09-04
Assumptions | 1. Tests marked 'cond. D1' apply only if backward Deal movement is approved.
2. D5 tests have no fixed expected result until the over-quota and sales-order ruling is recorded.
3. D7 decides whose approval threshold applies; the approval boundary tests inherit that answer.
4. Phase 1B and 1C assume the preceding release passed its own P1 tests.

## Test Plan
Test plan — WeQuote CRM Phase 1
How this release is tested, by whom, in what order, and what has to be true before it ships.
Objectives
• Prove the Deal stage is always derived from quotes and can never be typed in.
• Prove one customer account can never read or change another's records.
• Prove an Automation cannot approve, send, accept, or decide Won or Lost.
• Prove money figures — signed value, change orders, margin — agree with the quotes behind them.
• Prove each release can ship on its own without waiting for the next.
In scope
• Lead, Deal, Customer, Company and Activity records.
• Quote-to-stage logic, alternative groups and change orders.
• Deal value and the four margin figures.
• Managed recipes, their settings, scheduling and results.
• The advanced builder: catalogue, editing, testing, publishing, required work.
• Company-level visibility and account isolation.
Out of scope
• Forecast dashboards and weighted probability — Phase 2.
• Customer-created custom stages — Phase 2.
• Fully custom pipelines — Phase 3.
• Public web-to-lead forms — deferred.
• Zoho, QuickBooks and Xero behaviour beyond the coexistence rule in §C3.
Test levels
• Component: stage logic, quote-inclusion test, value arithmetic — automated.
• Integration: quote event to Deal update to Automation run — automated.
• System: the end-to-end journeys on the Use Case Coverage sheet — manual.
• UAT: the same journeys run by Sales and an Admin on staging.
• Regression: the six locked rules, re-run in full before every release.
Approach
• Automate anything the PRD names as automated: the precedence ladder, the quote-inclusion clauses, both revision flags, idempotency and account isolation.
• Everything else is manual, with evidence attached.
• Each test records its Method so automated coverage can be proven, not asserted.
Environment
• Staging, refreshed from a masked production copy before each release cycle.
• Build or commit recorded against every executed test.
• Timed recipes need the work queue running; note in Actual result if it was not.
Test accounts
• Audio Vision Group with at least three companies, for company-scope tests.
• A second unrelated account, for isolation tests.
• One Sales user limited to one company, one manager across all, one user with no CRM access.
• An approver distinct from the quote owner, for the high-value approval tests.
Test data
• A Deal with three quotes in one alternative group.
• A Deal with two independent quotes.
• A quote family whose latest revision is not the active one.
• One sample, one template and one archived quote.
• An accepted quote with a signed change order.
• At least one non-Sales pipeline with its own Deals.
Entry criteria
• The build is deployed to staging and smoke-passes.
• The release's blocking Delivery gate items for Decisions and Data are Done.
• Test data above is present.
• Known defects from the previous cycle are triaged.
Exit criteria
• Every P1 test for that release is Pass, or N/A with a reason and an approver.
• No open defect of severity 1 or 2.
• Every Blocking gate item for that release is Done.
• Automated tests named in the PRD are running in CI with a link recorded.
Roles
• QA runs the cases and records results.
• Engineering fixes defects and provides the CI links.
• Product decides on N/A waivers and answers the open decisions.
• Design confirms the interface behaviour cases.
• CTO signs the release gate.
Defect severity
• S1 — data loss, cross-account leakage, or a wrong Deal stage or value. Blocks the release.
• S2 — a documented rule not enforced, or a protected action reachable. Blocks the release.
• S3 — wrong or missing feedback, recoverable. Fix or waive with an owner.
• S4 — cosmetic. Backlog.
Retest and regression
• A fixed defect is retested on the build that contains the fix.
• Any change to stage logic, value arithmetic or the block catalogue re-runs the whole Regression sheet.
• A hotfix re-runs Regression plus the affected area.
Risks
• The activity timeline is barely used today; adoption is unproven — see §A13 D3.
• Zoho-connected accounts must stay switched off until D2 is answered.
• Timed recipes depend on a work queue that does not exist yet.
• Backward Deal movement is conditional on D1; those tests stay N/A until it is answered.
Release verification
• After deploy, re-run the Regression sheet on production data for one pilot account.
• Confirm the pipeline board, one Deal's value, and one recipe run.
• Rollback plan: disable the CRM navigation entry; no data migration is reversed automatically.

## Summary
Release gates
A release is clear when no P1 test is Fail, Blocked or Not run. Pass and N/A do not block; an N/A needs a reason and an approver.
Release | Total | Pass | Fail | Blocked | N/A | Not run | P1 blocking | Verdict
Phase 1A
Phase 1B
Phase 1C
Recipe coverage
Phase 1 programme
N/A hygiene
N/A without a waiver approver
Every N/A must carry a reason in Notes and an approver in 'Waiver approved by'.

## Delivery gate
Delivery gate — Phase 1
Extracted from §A14 of the PRD. Each release has its own gate; blocking items stop that release only.
ID | Release | Area | Item | Role | Gate | Owner | Status | Target date | Evidence / link
G-01 | Phase 1A | Decisions closed | D1 — do Deals move backwards? Until this is answered, FR-24 is not committed scope. | Product | Blocking |  | Not started
G-02 | Phase 1A | Decisions closed | D2 — Zoho coexistence. Deals stay switched off for Zoho-connected organisations until agreed. | Product + CTO | Blocking |  | Not started
G-03 | Phase 1A | Decisions closed | D4 — is the CRM company the existing Trading Name, or a new record? | Product + Eng | Blocking |  | Not started
G-04 | Phase 1A | Decisions closed | D5 — do over-quota quotes and sales orders count toward a Deal stage? | Product | Blocking |  | Not started
G-05 | Phase 1A | Decisions closed | D6 — does raising a change order follow the quote review path? | Product | Blocking |  | Not started
G-06 | Phase 1A | Decisions closed | D3 — why is today's activity timeline unused? Research complete, findings applied to the design. | Product + Design | Blocking |  | Not started
G-07 | Phase 1A | Data | Quote stage history extended to record the review stages it currently cannot. | Data | Blocking |  | Not started
G-08 | Phase 1A | Data | Activity timeline carries an organisation column, filled in for existing rows. | Data | Blocking |  | Not started
G-09 | Phase 1A | Data | Owning company assigned to existing quotes that have none. | Data | Blocking |  | Not started
G-10 | Phase 1A | Data | Ruling recorded on whether Deals are created for existing quotes, or only for new work. | Product + Eng | Blocking |  | Not started
G-11 | Phase 1A | Data | Default Lead states and disqualify reasons seeded per organisation. | Data | Track |  | Not started
G-12 | Phase 1A | Build | Stage logic derives every stage; no screen lets a person set one. | Engineering | Blocking |  | Not started
G-13 | Phase 1A | Build | Phase 1A creates no note, task, file request or notification unprompted (FR-41). | Engineering | Blocking |  | Not started
G-14 | Phase 1A | Build | Company-level visibility shipped as a real permission tier, not a filter. | Engineering | Blocking |  | Not started
G-15 | Phase 1A | Build | Account is established and checked when an event arrives, not from a signed-in session. | Engineering | Blocking |  | Not started
G-16 | Phase 1A | Build | Alternative groups, change orders, signed value and the four margin figures all present. | Engineering | Blocking |  | Not started
G-17 | Phase 1A | Tests | All eight precedence rules, each proven in isolation. | QA | Blocking |  | Not started
G-18 | Phase 1A | Tests | Each of the seven quote-inclusion clauses proven to exclude. | QA | Blocking |  | Not started
G-19 | Phase 1A | Tests | Both revision flags tested in all four combinations. | QA | Blocking |  | Not started
G-20 | Phase 1A | Tests | An event carrying another account's identifiers is rejected. | QA | Blocking |  | Not started
G-21 | Phase 1A | Flags | Site Ready custom stage hidden until Phase 2. | Engineering | Blocking |  | Not started
G-22 | Phase 1A | Flags | Commit Forecast and Stage-weighted views hidden until Phase 2. | Engineering | Blocking |  | Not started
G-23 | Phase 1A | Handoff | Conflict register (§C1) signed off, every row resolved or explicitly deferred. | Product | Blocking |  | Not started
G-24 | Phase 1A | Handoff | Margin definition written down: what each of the four figures includes. | Product | Track |  | Not started
G-25 | Phase 1B | Decisions | D7 — whose approval threshold applies on a high-value quote. | Product | Blocking |  | Not started
G-26 | Phase 1B | Build | One shared description of a flow, with versions stored server-side. Browser storage does not satisfy this. | Engineering | Blocking |  | Not started
G-27 | Phase 1B | Build | Recipe settings can be changed without opening the canvas. | Engineering | Blocking |  | Not started
G-28 | Phase 1B | Build | Every recipe carries a company scope, visible everywhere it is listed. | Engineering | Blocking |  | Not started
G-29 | Phase 1B | Build | Timed recipes have a real work queue: persistence, worker, working days, timezone, cancellation when a record leaves the stage. | Engineering | Blocking |  | Not started
G-30 | Phase 1B | Tests | Replaying the same event creates nothing twice, for every action type. | QA | Blocking |  | Not started
G-31 | Phase 1B | Tests | Work already in flight finishes on the version it started with. | QA | Blocking |  | Not started
G-32 | Phase 1B | Tests | Only one change order can be open per quote. | QA | Blocking |  | Not started
G-33 | Phase 1B | Handoff | All twelve recipes are defined and configurable. A timed recipe cannot be switched on until the production work queue exists. | Product | Blocking |  | Not started
G-34 | Phase 1B | Handoff | Event-driven recipes ship first. Timed recipes stay unavailable, not merely inactive, until the queue lands. | Engineering | Track |  | Not started
G-35 | Phase 1C | Build | The block list is built from one shared source. No per-stage hard-coded lists, and placement never used as a permission key (FR-33). | Engineering | Blocking |  | Not started
G-36 | Phase 1C | Build | Draft, optional test and publish, with publishing blocked only by a real conflict. | Engineering | Blocking |  | Not started
G-37 | Phase 1C | Build | Required-work gate collects every outstanding item and resumes the exact original action. | Engineering | Blocking |  | Not started
G-38 | Phase 1C | Tests | The shared core block list is identical in all seven protected stages. Stage-specific quote events and rules appear only where they can genuinely occur. | QA | Blocking |  | Not started
G-39 | Phase 1C | Tests | A draft or test never changes the live version. | QA | Blocking |  | Not started
G-40 | Phase 1C | Handoff | "Open as an editable copy" documented as one-way, with no promise of returning to the simple form. | Design | Track |  | Not started
Gate by release
Release | Total | Done | Blocking outstanding | Verdict
Phase 1A
Phase 1B
Phase 1C
Rows missing Owner or Target date
Every gate row needs a named owner and a target date before the release is planned.

## Traceability
Traceability — locked rule to evidence
One row per link. Status is live: it reads the QA case's own result. A rule is only proven when every linked case passes.
Rule | Statement | Requirement | Acceptance criterion | QA sheet | QA case | Delivery gate | Applies from | Live status | Gap / note
1 | Creating the first related quote moves the Deal from Qualified to In Progress. | — (no FR states the transition) | AC-DEAL-01 | Phase 1A | 1A-08 | G-12 | Phase 1A |  | GAP: the transition is stated in §A6 and tested, but no functional requirement carries it. Add one, or cite §A6 explicitly.
|  |  |  | Regression | REG-01
2 | Any relevant quote being accepted makes the Deal Won. Remaining groups change the signed value, never the stage. | FR-16, FR-17 | AC-DEAL-01, AC-DEAL-07 | Phase 1A | 1A-14 | G-17 | Phase 1A
|  |  |  | Phase 1A | 1A-15
|  |  |  | Phase 1A | 1A-16
|  |  |  | Phase 1A | 1A-17
|  |  |  | Regression | REG-02
3 | Sales supplies the loss reason. Sales does not decide the Lost outcome; the system derives it. | — (FR-17 covers Won and Archived only) | AC-DEAL-01 | Phase 1A | 1A-19 | G-17 | Phase 1A |  | GAP: no FR separates deriving the outcome from supplying the reason. §A6 and §A7 both state it; a requirement should too.
|  |  |  | Regression | REG-03
4 | Testing is optional. Only a real conflict blocks publishing. | FR-13 | AC-BLD-10 | Phase 1C | 1C-18 | G-36 | Phase 1C
|  |  |  | Regression | REG-04
5 | A Phase 2 custom stage receives the identical core block library wherever it sits. | FR-06, FR-33 | AC-BLD-05 | Phase 1C | 1C-06 | G-35, G-38 | Phase 2 |  | REG-05 cannot run before Phase 2. It is excluded from the Phase 1 gates by its Applies from value.
|  |  |  | Phase 1C | 1C-09
|  |  |  | Regression | REG-05
6 | A protected quote lifecycle event is never an ordinary Automation action. | FR-08 | AC-BLD-07 | Phase 1C | 1C-08 | G-12 | Phase 1A
|  |  |  | Regression | REG-06
Linked cases passing
Requirement gaps
A locked rule is only safe once every linked QA case passes AND its delivery gate item is Done. The two gaps are documentation gaps, not test gaps — both rules are tested.

## Use Case Coverage
Use case coverage
End-to-end journeys, each mapped to the granular cases that make it up. Coverage is live: it reads those cases' results.
ID | Use case | Phase | Persona | Journey | Test IDs | Cases | Passing | Coverage | Notes
UC-01 | Lead to first quote | Phase 1A | Sales | New Lead → duplicate check → customer linked → convert → Deal in Qualified → create first quote → In Progress | 1A-01, 1A-02, 1A-08 | 3
UC-02 | Full review path | Phase 1A | Sales + Reviewer | In Progress → submit → In Review → pass → Passed Review → send → Sent | 1A-09, 1A-10, 1A-11 | 3
UC-03 | No-review path | Phase 1A | Sales | Review disabled → In Progress → send → Sent, skipping both review stages | 1A-12 | 1
UC-04 | Changes requested | Phase 1A | Reviewer | In Review → changes requested → back to In Progress → resubmit | 1A-13, 1A-09 | 2
UC-05 | Client engagement | Phase 1A | Sales | Three quotes sent → client opens two → Deal card shows 2 of 3 viewed | 1A-31, 1A-30, 1A-32 | 3
UC-06 | Win the deal | Phase 1A | Sales | Alternative group of three → accept one → siblings rejected → Deal Won → value locked | 1A-16, 1A-14, 1A-45 | 3
UC-07 | Lose the deal | Phase 1A | Sales | All quotes expire → Lost derived → Sales supplies the loss reason | 1A-19 | 1
UC-08 | Work called off | Phase 1A | Sales | All quotes cancelled → Deal Archived, not Lost | 1A-18 | 1
UC-09 | Additive versus competing | Phase 1A | Sales | Two independent quotes add up; two grouped quotes compete | 1A-34, 1A-35, 1A-37 | 3
UC-10 | Vary sold work | Phase 1A | Sales + Finance | Accepted quote → raise change order → client signs → value updated, stage unchanged | 1A-38, 1A-40, 1A-42 | 3
UC-11 | Multi-company working | Phase 1A | Manager | Audio Vision manager sees permitted companies only; scoped Automation runs for one branch | 1A-47, 1B-04 | 2
UC-12 | Switch on a recipe | Phase 1B | Admin | Choose a recipe → set owner, days and scope → activate → it fires and writes to the Deal card | 1B-01, 1B-02, 1B-20 | 3
UC-13 | Chase a sent quote | Phase 1B | Sales | Quote sent → wait three working days → follow-up note created and visible | 1B-09, 1B-21 | 2
UC-14 | High-value approval | Phase 1B | Sales + Approver | Quote passes review above threshold → approval note raised to the approver | 1B-16, 1B-17 | 2
UC-15 | Draft to publish | Phase 1C | Admin | Open → edit → save draft → test → validate → publish → history recorded | 1C-12, 1C-16, 1C-20, 1C-30 | 4
UC-16 | Blocked publish | Phase 1C | Admin | Introduce a conflict → publishing refused with the step named → fix → publish succeeds | 1C-21, 1C-20 | 2
UC-17 | Required work before a move | Phase 1C | Sales | Attempt a stage move → outstanding items listed → resolve inline → original action resumes | 1C-33, 1C-32 | 2
UC-18 | Right pipeline every time | Phase 1C | Admin | Deal on a non-Sales pipeline → open its Automations from the Deal page → correct pipeline opens | 1C-05, 1C-03, 1C-04 | 3
Journeys fully covered

## Phase 1A
QA checklist — Phase 1A
CRM foundation — records, stage logic, alternatives, change orders, value, visibility and tenancy.
Fill in from Status onwards. Everything to the left describes the test.
ID | Release | Applies from | Area | Pri | Method | Precondition | Steps | Expected result | Traces to | Status | Actual result | Build | Environment | Browser / device | Test data | Evidence link | Defect ID | Waiver approved by | Tester | Date | Notes
1A-01 | Phase 1A | Phase 1A | Lead | P1 | Manual | A customer named Hillside Residence already exists. | Create a Lead for 'Hillside Residence'. | Possible matches are shown before saving. The user must pick one or explicitly create new. No customer is created silently. | FR-27 / AC-LEAD-01 | Not run
1A-02 | Phase 1A | Phase 1A | Lead | P1 | Manual | An open Lead exists. | Convert the Lead to a Deal. | Exactly one Deal is created, in Qualified. The Lead becomes converted and read-only. | FR-28 / AC-LEAD-02, AC-LEAD-03 | Not run
1A-03 | Phase 1A | Phase 1A | Lead | P2 | Manual | A converted Lead exists. | Attempt to convert it again. | Rejected. A message names the Deal that already exists and links to it. No second Deal is created. | AC-LEAD-03 | Not run
1A-04 | Phase 1A | Phase 1A | Lead | P1 | Manual | An open Lead exists. | Discard it without choosing a reason. | Discard is refused. The reason field is marked required and the Lead stays open until one is chosen. | AC-LEAD-04 | Not run
1A-05 | Phase 1A | Phase 1A | Lead | P1 | Manual | An open Lead exists. | Try every route to attach a quote to the Lead. | No route exists — not from the Lead, not from the quote list, not by direct URL. A quote can only attach to a Deal. | FR-26 / AC-LEAD-05 | Not run
1A-06 | Phase 1A | Phase 1A | Lead | P2 | Manual | Leads across several companies. | Filter the Lead inbox by company. | Only Leads whose owning company matches the filter are listed. The count in the header matches the rows shown. | FR-38 / C15 | Not run
1A-07 | Phase 1A | Phase 1A | Resolver | P1 | Automated | A Deal with no related quote. | Inspect the Deal stage. | The Deal reads Qualified. No stage control is offered to the user. | AC-DEAL-01 | Not run
1A-08 | Phase 1A | Phase 1A | Resolver | P1 | Automated | A Deal in Qualified. | Create the first related quote. | The Deal moves to In Progress. No screen offers a manual move. | Locked rule 1 | Not run
1A-09 | Phase 1A | Phase 1A | Resolver | P1 | Automated | A draft quote; quote review enabled. | Submit the quote for review. | The Deal moves to In Review, the history records the trigger, and no other Deal is affected. | AC-DEAL-01 | Not run
1A-10 | Phase 1A | Phase 1A | Resolver | P1 | Automated | A quote in review. | Reviewer passes the quote. | The Deal moves to Passed Review and the history records who passed it and when. | AC-DEAL-01 | Not run
1A-11 | Phase 1A | Phase 1A | Resolver | P1 | Automated | A quote that passed review. | Send the quote to the client. | The Deal moves to Sent and the sent date is recorded against the quote. | AC-DEAL-01 | Not run
1A-12 | Phase 1A | Phase 1A | Resolver | P1 | Automated | Quote review DISABLED for the organisation. | Send a quote directly from In Progress. | The Deal moves straight to Sent. In Review and Passed Review never appear. | A6 / FR-12 | Not run
1A-13 | Phase 1A | Phase 1A | Resolver | P1 | Automated | A quote in review. | Reviewer requests changes. | The Deal returns to In Progress. The history records the reason as changes requested, and the quote is editable again. | A6 | Not run
1A-14 | Phase 1A | Phase 1A | Resolver | P1 | Automated | A Deal with a quote in state Accepted. | Inspect the Deal stage. | The Deal reads Won. The accepted quote is marked as the winner and the signed value is locked to its amount. | Locked rule 2 / AC-DEAL-01 | Not run
1A-15 | Phase 1A | Phase 1A | Resolver | P1 | Automated | A Deal with a quote in state Complete. | Inspect the Deal stage. | The Deal reads Won. Complete maps to Won exactly as Accepted does, with no difference in stage or value handling. | Locked rule 2 | Not run
1A-16 | Phase 1A | Phase 1A | Resolver | P1 | Automated | Three live quotes in one alternative group. | Accept one. | The Deal becomes Won immediately. The other two are system-rejected and stay in history. | Locked rule 2 / AC-DEAL-07 | Not run
1A-17 | Phase 1A | Phase 1A | Resolver | P1 | Automated | A Won Deal with another group unresolved. | Resolve the remaining group. | The signed value updates to include the newly resolved group. The stage stays Won and the history shows a value change, not a stage change. | Locked rule 2 | Not run
1A-18 | Phase 1A | Phase 1A | Resolver | P1 | Automated | Every related quote cancelled. | Inspect the Deal. | The Deal shows Archived as a status, not a stage. It is excluded from win-rate reporting and does not appear as Lost. | AC-DEAL-02 | Not run
1A-19 | Phase 1A | Phase 1A | Resolver | P1 | Automated | Two sent quotes, both expired. | Inspect the Deal. | Lost, derived. Sales is asked for a reason; supplying it does not change the outcome. | Locked rule 3 | Not run
1A-20 | Phase 1A | Phase 1A | Resolver | P1 | Automated | Mixed: Q1 cancelled, Q2 expired, Q3 draft. | Inspect the Deal stage. | In Progress. Q3 is the only quote that still qualifies. | AC-DEAL-01 | Not run
1A-21 | Phase 1A | Phase 1A | Resolver | P1 | Automated | A Deal with one sample quote only. | Inspect the Deal stage. | The sample quote is ignored entirely. The Deal reads Qualified and the sample does not appear in the Deal's quote count. | AC-DEAL-04 | Not run
1A-22 | Phase 1A | Phase 1A | Resolver | P1 | Automated | A Deal with one template quote only. | Inspect the Deal stage. | The template quote is ignored entirely. The Deal reads Qualified and the template does not appear in the Deal's quote count. | AC-DEAL-04 | Not run
1A-23 | Phase 1A | Phase 1A | Resolver | P1 | Automated | A Deal with one archived quote only. | Inspect the Deal stage. | The archived quote is ignored entirely. The Deal reads Qualified and the archived quote does not appear in the Deal's quote count. | AC-DEAL-04 | Not run
1A-24 | Phase 1A | Phase 1A | Resolver | P1 | Automated | Latest revision is NOT the active one. | Inspect the Deal stage. | No stage derives from it. Only latest AND active counts. | AC-DEAL-05 | Not run
1A-25 | Phase 1A | Phase 1A | Resolver | P1 | Automated | Active revision is not the latest. | Inspect the Deal stage. | Neither revision qualifies, so the family contributes nothing. The Deal reads whatever the other families produce, or Qualified if there are none. | AC-DEAL-05 | Not run
1A-26 | Phase 1A | Phase 1A | Resolver | P1 | Automated | A sent quote and a draft quote. D1 answered yes. | Let the sent quote expire. | The Deal steps back to In Progress and the reason is written to history. | FR-24 (cond. D1) | Not run
1A-27 | Phase 1A | Phase 1A | Resolver | P2 | Manual | A Won Deal with an accepted quote. | Cancel or reopen the accepted quote. | Behaviour matches the final D1 ruling; the outcome is recorded either way. | D1 | Not run
1A-28 | Phase 1A | Phase 1A | Resolver | P2 | Manual | A Deal with an over-quota quote. | Inspect the Deal stage. | Behaviour matches the recorded D5 ruling, and whichever way it is ruled the Deal's stage and its quote count agree with each other. | D5 | Not run
1A-29 | Phase 1A | Phase 1A | Resolver | P2 | Manual | A Deal with a sales order. | Inspect the Deal stage. | Behaviour matches the recorded D5 ruling, and whichever way it is ruled the Deal's stage and its quote count agree with each other. | D5 | Not run
1A-30 | Phase 1A | Phase 1A | Engagement | P1 | Automated | Q1 sent and viewed, Q2 draft. | Read the viewed count. | The Deal card reads '1 of 1 sent quotes viewed'. The draft is excluded from the count on the right. | AC-DEAL-03 | Not run
1A-31 | Phase 1A | Phase 1A | Engagement | P1 | Automated | Q1 sent viewed, Q2 sent not viewed, Q3 sent viewed. | Read the viewed count. | The Deal card reads '2 of 3 sent quotes viewed'. | AC-DEAL-03 | Not run
1A-32 | Phase 1A | Phase 1A | Engagement | P1 | Automated | Q1 expired, Q2 sent not viewed. | Read the viewed count. | The Deal card reads '0 of 1 sent quotes viewed'. The expired quote is excluded from the count on the right. | AC-DEAL-03 | Not run
1A-33 | Phase 1A | Phase 1A | Engagement | P1 | Automated | A signed change order on a sent quote. | Read the viewed count. | The change order appears in neither number. Only client-facing quotes are counted. | FR-32 | Not run
1A-34 | Phase 1A | Phase 1A | Alternatives | P1 | Automated | Two ungrouped quotes on one Deal. | Inspect the Deal value. | Both quotes contribute to the Deal value, and the total equals their sum. | AC-DEAL-08 | Not run
1A-35 | Phase 1A | Phase 1A | Alternatives | P1 | Automated | Two quotes in one alternative group. | Accept one. | The sibling is system-rejected, removed from value, still in the audit trail. | AC-DEAL-07 | Not run
1A-36 | Phase 1A | Phase 1A | Alternatives | P1 | Manual | A quote already accepted inside a group. | Try to move it out of the group. | The move is refused, with a message explaining that a resolved quote cannot be regrouped. The group membership is unchanged. | FR-30 | Not run
1A-37 | Phase 1A | Phase 1A | Alternatives | P1 | Automated | Two groups, one accepted quote in each. | Inspect the Deal value. | The Deal value equals the sum of the two accepted amounts. Neither group's rejected siblings contribute. | AC-DEAL-08 | Not run
1A-38 | Phase 1A | Phase 1A | Change order | P1 | Manual | A quote with an accepted revision. | Raise a change order. | Raised against the accepted revision, which is the signed baseline. | A7 | Not run
1A-39 | Phase 1A | Phase 1A | Change order | P1 | Manual | A change order is with the client. | Raise a second one on the same quote. | Raising is refused. A message explains that one change order is already with the client, and names it. The existing one is untouched. | FR-31 / AC-DEAL-09 | Not run
1A-40 | Phase 1A | Phase 1A | Change order | P1 | Automated | A change order with the client. | Client signs it. | It becomes the new signed baseline; its difference is added to the signed value. | FR-31 / AC-DEAL-10 | Not run
1A-41 | Phase 1A | Phase 1A | Change order | P1 | Automated | A change order with the client. | Reject it. | It stops contributing to the signed totals. The signed value returns to what it was before the change order was raised, and the rejection is recorded in history. | FR-31 | Not run
1A-42 | Phase 1A | Phase 1A | Change order | P1 | Automated | A Won Deal with a signed change order. | Inspect stage and value. | Stage stays Won. Value includes the difference, shown separately from the accepted base. | AC-DEAL-06 | Not run
1A-43 | Phase 1A | Phase 1A | Change order | P2 | Manual | A quote carrying a signed change order. | Try to unlink the quote. | Unlinking is refused, with a message explaining that a quote carrying a signed change order cannot be removed from its Deal. | FR-34 | Not run
1A-44 | Phase 1A | Phase 1A | Value | P1 | Manual | A Deal with no linked quotes. | Inspect the Deal value. | The manual estimate is used and labelled as an estimate. | A7 | Not run
1A-45 | Phase 1A | Phase 1A | Value | P1 | Automated | A Won Deal. | Inspect the money panel. | Signed = accepted net totals plus change-order differences. Draft invoice value is separate and not inside invoiced. | FR-29 / A7 | Not run
1A-46 | Phase 1A | Phase 1A | Value | P2 | Manual | A Deal with quotes and change orders. | Inspect the four margin figures. | Deal, signed, product and labour margin all present, each stating its basis. | C20 | Not run
1A-47 | Phase 1A | Phase 1A | Visibility | P1 | Manual | Users in two companies; records in both. | Sign in as a user limited to one company. | Only that company's Leads, Deals and Automations are visible. | FR-38 / AC-BLD-04 | Not run
1A-48 | Phase 1A | Phase 1A | Visibility | P1 | Manual | A user who owns nothing and is on no team. | Open the Deal list. | The list is empty apart from anything explicitly shared. No Deal from another owner, team or company appears. | FR-38 | Not run
1A-49 | Phase 1A | Phase 1A | Visibility | P2 | Manual | Deals across companies and stages. | Apply pipeline, company and stage filters, then sort. | Basic filtering and sorting work. No forecast-specific control is present. | AC-RUN-07 | Not run
1A-50 | Phase 1A | Phase 1A | Tenancy | P1 | Automated | Two customer accounts with data. | Inject a quote event carrying the other account's identifiers. | Rejected the moment it is received, before any company or stage is matched. Nothing is written to either account. | FR-37 / AC-RUN-05 | Not run
1A-51 | Phase 1A | Phase 1A | Tenancy | P1 | Automated | Two accounts, each with activity entries. | Read the activity timeline as each account. | Each sees only its own. The organisation column is populated on every row including pre-existing ones. | FR-39 | Not run
1A-52 | Phase 1A | Phase 1A | No side effects | P1 | Manual | Phase 1A build, no recipes configured. | Move a Deal through every stage, leave it idle a week, let a quote expire. | No note, task, file request or notification is created unprompted. Needs-your-attention may display but must not write. | FR-41 | Not run
1A-53 | Phase 1A | Phase 1A | Flags | P1 | Manual | Phase 1A build. | Look for Site Ready, Commit Forecast and Stage-weighted views. | None of the three is reachable — not in navigation, not by direct URL, and not through search. | D8 | Not run
1A-54 | Phase 1A | Phase 1A | History | P1 | Manual | A Deal that moved through several stages. | Open the Deal history. | Every protected transition recorded with its trigger; every backward correction records its reason. | AC-DEAL-01 | Not run

## Phase 1B
QA checklist — Phase 1B
Managed recipes — settings without the canvas, versioning, idempotency, timed work, approvals and Deal-card output.
Fill in from Status onwards. Everything to the left describes the test.
ID | Release | Applies from | Area | Pri | Method | Precondition | Steps | Expected result | Traces to | Status | Actual result | Build | Environment | Browser / device | Test data | Evidence link | Defect ID | Waiver approved by | Tester | Date | Notes
1B-01 | Phase 1B | Phase 1B | Recipe setup | P1 | Manual | Phase 1B build. | Enable a recipe and change owner, wait days and label. | Every exposed setting can be changed and saved from the recipe form. The canvas is never opened, and the saved values are reflected the next time the recipe runs. | FR-02 | Not run
1B-02 | Phase 1B | Phase 1B | Recipe setup | P1 | Manual | Creating a recipe. | Save without choosing a company scope. | Blocked. Scope is required and defaults to All Companies. | FR-09 / AC-BLD-04 | Not run
1B-03 | Phase 1B | Phase 1B | Recipe setup | P2 | Manual | A recipe with company scope set. | Check every surface that lists it. | Scope visible in list, editor, comparison, publish and history. | FR-10 | Not run
1B-04 | Phase 1B | Phase 1B | Recipe setup | P1 | Automated | A recipe scoped to one company. | Trigger the matching event in another company. | The recipe does not run. No note, task or notification is created, and nothing is written to that Deal's history. | FR-15 / AC-RUN-06 | Not run
1B-05 | Phase 1B | Phase 1B | Versioning | P1 | Automated | A published recipe. | Change a setting and save without publishing. | The live version keeps running. The change is held as a draft. | FR-11 / AC-BLD-08 | Not run
1B-06 | Phase 1B | Phase 1B | Versioning | P1 | Automated | A recipe with work already waiting. | Publish a new version. | Work in flight finishes on the version it started with. | A15 | Not run
1B-07 | Phase 1B | Phase 1B | Versioning | P1 | Manual | Phase 1B build. | Restart the server, then read a saved recipe and its versions. | The recipe and all its versions load exactly as before the restart. Nothing depended on the browser, and any work that was waiting is still waiting. | FR-40 | Not run
1B-08 | Phase 1B | Phase 1B | Idempotency | P1 | Automated | A recipe creating a note, a next action and a file request. | Replay the same source event three times. | Exactly one note, one next action and one file request exist. The run history shows three receipts of the same event and two of them recorded as already handled. | FR-21 / AC-RUN-04 | Not run
1B-09 | Phase 1B | Phase 1B | Timed work | P1 | Automated | Sent quote follow-up, three working days. | Send a quote on a Friday. | Fires the following Wednesday, counting working days only. | FR-36 | Not run
1B-10 | Phase 1B | Phase 1B | Timed work | P1 | Automated | A recipe waiting on a Deal. | Move the Deal out of the stage before the wait ends. | The pending run is cancelled or revalidated; it does not fire against the wrong stage. | FR-36 | Not run
1B-11 | Phase 1B | Phase 1B | Timed work | P2 | Automated | A wait spanning a daylight-saving change. | Let the wait elapse. | It fires at the intended local time, not an hour early or late. | FR-36 | Not run
1B-12 | Phase 1B | Phase 1B | Timed work | P1 | Manual | Event-driven recipes only; work queue not yet built. | Trigger a quote-sent recipe. | It runs. Event-driven recipes are not blocked by the queue. | FR-36 | Not run
1B-13 | Phase 1B | Phase 1B | Timed work | P1 | Manual | Work queue not yet built. | Try to switch on a timed recipe. | The recipe cannot be switched on at all. It is shown as unavailable with the reason given, rather than offered as an inactive toggle. | A14 | Not run
1B-14 | Phase 1B | Phase 1B | Approval | P1 | Automated | High-value approval; value threshold GBP 25,000. | Pass review on a quote of GBP 24,999. | No approval note is raised, and the quote proceeds normally. | D7 | Not run
1B-15 | Phase 1B | Phase 1B | Approval | P1 | Automated | Same threshold. | Pass review on a quote of exactly GBP 25,000. | Behaviour matches the documented boundary rule, and the rule is stated in the recipe. | D7 | Not run
1B-16 | Phase 1B | Phase 1B | Approval | P1 | Automated | Same threshold. | Pass review on a quote of GBP 25,001. | An approval note is raised to the approver named by D7. | D7 | Not run
1B-17 | Phase 1B | Phase 1B | Approval | P1 | Automated | Discount threshold 15%. | Pass review on a quote at 16% discount but below the value threshold. | An approval note is raised. The OR condition fires on either limb. | D7 | Not run
1B-18 | Phase 1B | Phase 1B | Approval | P1 | Automated | Both thresholds exceeded. | Pass review. | Exactly one approval note is raised, not one per limb of the condition. | D7 | Not run
1B-19 | Phase 1B | Phase 1B | Approval | P2 | Manual | An approval already configured. | Change the configured threshold and re-run. | The new threshold applies. Existing pending work is unaffected. | D7 | Not run
1B-20 | Phase 1B | Phase 1B | Deal card | P1 | Manual | A recipe that schedules a meeting on a Qualified Deal. | Let it run. | The meeting appears on the Deal card AND in Deal activity, not only in history. | FR-22 / AC-RUN-03 | Not run
1B-21 | Phase 1B | Phase 1B | Deal card | P1 | Manual | A recipe that sets a next action. | Let it run. | The next action, its owner and its due date appear on the Deal card. | FR-22 | Not run
1B-22 | Phase 1B | Phase 1B | Deal card | P1 | Manual | A note with a follow-up. | Let it run. | The follow-up appears on the Deal card and in activity. | FR-22 | Not run
1B-23 | Phase 1B | Phase 1B | Deal card | P1 | Manual | A recipe that requests a file. | Let it run. | The request appears in Needs your attention and on the Deal card, with due date and assignee. | FR-20 / FR-22 | Not run
1B-24 | Phase 1B | Phase 1B | Deal card | P2 | Manual | A Deal with an expected close date. | Open Deal details. | Expected close date appears under Labels, not as a Lead field. | A11 | Not run
1B-25 | Phase 1B | Phase 1B | Deal card | P1 | Manual | An outstanding file request on a Deal card. | Upload the matching file. | Card, activity, focus and history all clear or update together. | FR-20 | Not run

## Recipe coverage
Recipe coverage matrix
Each of the twelve ready-made recipes, against nine checks. Every cell is a test result.
ID | Recipe | Stage | Kind | Correct trigger | Rule Yes path | Rule No path | Correct action | Company scope | Active / Inactive | Output in right place | History entry | Retry no duplicate | Notes
RC-01 | Qualified first next action | Qualified | Event | Not run | Not run | Not run | Not run | Not run | Not run | Not run | Not run | Not run
RC-02 | Qualified inactivity reminder | Qualified | Timed | Not run | Not run | Not run | Not run | Not run | Not run | Not run | Not run | Not run
RC-03 | Site visit & pre-quote readiness | Qualified | Event | Not run | Not run | Not run | Not run | Not run | Not run | Not run | Not run | Not run
RC-04 | Quote build and scope-of-work checks | In Progress | Event | Not run | Not run | Not run | Not run | Not run | Not run | Not run | Not run | Not run
RC-05 | Internal quote review | In Review | Event | Not run | Not run | Not run | Not run | Not run | Not run | Not run | Not run | Not run
RC-06 | Ready-to-send check | Passed Review | Event | Not run | Not run | Not run | Not run | Not run | Not run | Not run | Not run | Not run
RC-07 | High-value approval | Passed Review | Event | Not run | Not run | Not run | Not run | Not run | Not run | Not run | Not run | Not run
RC-08 | Sent quote follow-up | Sent | Timed | Not run | Not run | Not run | Not run | Not run | Not run | Not run | Not run | Not run
RC-09 | Quote expiry reminder | Sent | Timed | Not run | Not run | Not run | Not run | Not run | Not run | Not run | Not run | Not run
RC-10 | Won Deal handoff | Won | Event | Not run | Not run | Not run | Not run | Not run | Not run | Not run | Not run | Not run
RC-11 | Accepted quote to draft invoice | Won | Event | Not run | Not run | Not run | Not run | Not run | Not run | Not run | Not run | Not run
RC-12 | Lost Deal reason follow-up | Lost | Event | Not run | Not run | Not run | Not run | Not run | Not run | Not run | Not run | Not run
Cells outstanding

## Phase 1C
QA checklist — Phase 1C
Advanced builder — navigation, catalogue, editing flow, simulator, publishing, state and required work.
Fill in from Status onwards. Everything to the left describes the test.
ID | Release | Applies from | Area | Pri | Method | Precondition | Steps | Expected result | Traces to | Status | Actual result | Build | Environment | Browser / device | Test data | Evidence link | Defect ID | Waiver approved by | Tester | Date | Notes
1C-01 | Phase 1C | Phase 1C | Creation | P1 | Manual | Phase 1C build. | Open Create Automation. | Exactly two routes: start from a recipe, or start from scratch. | FR-01 / AC-BLD-03 | Not run
1C-02 | Phase 1C | Phase 1C | Creation | P1 | Manual | A pipeline with no Automations. | Open it. | Opens to an empty state that explains the situation and offers Create Automation. | FR-23 / AC-BLD-02 | Not run
1C-03 | Phase 1C | Phase 1C | Navigation | P1 | Manual | Deals shows more than one pipeline, including a non-Sales one. | Open the Automation pipeline chooser. | Every pipeline that appears in Deals is listed in the chooser, with the same names and in a predictable order. | AC-BLD-01 | Not run
1C-04 | Phase 1C | Phase 1C | Navigation | P1 | Manual | A non-Sales pipeline exists. | Choose it from the chooser. | That pipeline opens. It never falls back to Sales Pipeline. | AC-BLD-01 | Not run
1C-05 | Phase 1C | Phase 1C | Navigation | P1 | Manual | A Deal belonging to a non-Sales pipeline. | Click the Automation status control on the Deal page. | That Deal's own pipeline opens, focused on the right stage. It never falls back to Sales Pipeline. | AC-BLD-01 | Not run
1C-06 | Phase 1C | Phase 1C | Catalogue | P1 | Automated | The builder open in each of the seven stages. | Compare the offered blocks. | The shared core is identical in all seven. Only quote-specific additions differ. | FR-06 / AC-BLD-05 | Not run
1C-07 | Phase 1C | Phase 1C | Catalogue | P1 | Manual | The builder open in In Progress. | Look for a Lead-only trigger. | The incompatible trigger is visible but struck through and cannot be selected. A short reason explains why it does not apply here. | FR-11 / AC-BLD-06 | Not run
1C-08 | Phase 1C | Phase 1C | Catalogue | P1 | Manual | The builder on any stage. | Try to add an action that sets a Deal stage. | No such action exists anywhere in the catalogue — not under a different name, and not behind a search. | FR-08 / AC-BLD-07 | Not run
1C-09 | Phase 1C | Phase 1C | Catalogue | P1 | Automated | Phase 1C build. | Inspect how the block list is produced. | One shared source. No per-stage hard-coded lists; placement is not a permission key. | FR-33 | Not run
1C-10 | Phase 1C | Phase 1C | Builder | P2 | Manual | An Automation created from In Progress. | Try to change its stage in the builder. | The stage selector is read-only and shows why: the Automation was created from that stage. | A9 | Not run
1C-11 | Phase 1C | Phase 1C | Editing | P1 | Manual | A published Automation, nothing changed. | Look at Save Draft. | Disabled. Before & After shows 'no unpublished changes', not two identical panes. | AC-BLD-11 | Not run
1C-12 | Phase 1C | Phase 1C | Editing | P1 | Manual | A published Automation. | Change one step. | 'Unpublished changes' appears, and Before & After compares published with draft. | AC-BLD-11 | Not run
1C-13 | Phase 1C | Phase 1C | Editing | P1 | Manual | A draft that passed a test. | Edit it again. | The state becomes 'Test outdated'. Publishing is still allowed if validation is clean. | FR-13 / AC-BLD-10 | Not run
1C-14 | Phase 1C | Phase 1C | Editing | P1 | Manual | A draft with unsaved changes. | Exit the builder. | Offered Continue editing, Discard changes, and Save draft & exit. | A11 | Not run
1C-15 | Phase 1C | Phase 1C | Editing | P2 | Manual | A draft with no unsaved changes. | Exit the builder. | The builder closes immediately with no prompt, and nothing is saved or discarded. | A11 | Not run
1C-16 | Phase 1C | Phase 1C | Simulator | P1 | Manual | A draft ready to test. | Run a test. | Timeline opens as the default tab. No live CRM record is created, changed or deleted, and the result says so explicitly. | FR-12 / AC-BLD-09 | Not run
1C-17 | Phase 1C | Phase 1C | Simulator | P1 | Manual | A test running. | Use Play, Step, Reset and Speed. | Play runs the flow, Step advances one step, Reset returns to the start and Speed changes the playback rate. All four respond. | AC-BLD-09 | Not run
1C-18 | Phase 1C | Phase 1C | Publish | P1 | Manual | A valid draft, never tested. | Publish it. | Publishing succeeds. A missing or outdated test does not block it, and the published version is recorded. | FR-13 / AC-BLD-10 | Not run
1C-19 | Phase 1C | Phase 1C | Publish | P1 | Manual | A draft ready to publish. | Open the publish confirmation. | It shows Before & After, the company scope and the test status. | A11 | Not run
1C-20 | Phase 1C | Phase 1C | Publish | P1 | Manual | A draft ready to publish. | Publish it. | The live version is replaced in one step and the previous version recorded. | FR-14 | Not run
1C-21 | Phase 1C | Phase 1C | Publish | P1 | Manual | An action missing required configuration. | Try to publish. | Publishing is blocked. The offending step is highlighted, the reason names the missing configuration, the draft stays saved, and the live version keeps running unchanged. | A11 | Not run
1C-22 | Phase 1C | Phase 1C | Publish | P1 | Manual | A deleted target stage referenced. | Try to publish. | Publishing is blocked. The step referencing the deleted stage is highlighted, the draft stays saved, and the live version keeps running unchanged. | A11 | Not run
1C-23 | Phase 1C | Phase 1C | Publish | P1 | Manual | A file-received trigger pointing at a removed request. | Try to publish. | Publishing is blocked. The trigger is highlighted with a reason naming the missing file request, the draft stays saved, and the live version keeps running unchanged. | A11 | Not run
1C-24 | Phase 1C | Phase 1C | Publish | P1 | Manual | A branch that loops back on itself. | Try to publish. | Publishing is blocked. The looping branch is highlighted, the reason explains the cycle, the draft stays saved, and the live version keeps running unchanged. | A11 | Not run
1C-25 | Phase 1C | Phase 1C | Publish | P1 | Manual | A protected milestone used as a move target. | Try to publish. | Publishing is blocked. The move step is highlighted with a reason stating that protected milestones cannot be a move target, and the live version keeps running unchanged. | A11 | Not run
1C-26 | Phase 1C | Phase 1C | Publish | P1 | Manual | A wait that cannot end. | Try to publish. | Publishing is blocked. The wait step is highlighted with a reason stating it has no safe ending, and the live version keeps running unchanged. | A11 | Not run
1C-27 | Phase 1C | Phase 1C | State | P1 | Manual | A published Automation. | Toggle it Active then Inactive. | The change takes effect immediately: an inactive Automation stops running, and both Map and List show the new state. | FR-15 / AC-BLD-12 | Not run
1C-28 | Phase 1C | Phase 1C | State | P1 | Manual | A pipeline with several Automations. | Pause then resume at pipeline level. | All Automations in the pipeline follow. The counts on Map and List stay in step. | A9 | Not run
1C-29 | Phase 1C | Phase 1C | State | P2 | Manual | Pipeline paused with impact comparison shown. | Compare it with a single-Automation test. | The two are visibly different features and are not confused in the interface. | A11 | Not run
1C-30 | Phase 1C | Phase 1C | History | P1 | Manual | An Automation published twice. | Open change history. | Each entry records the version, the company scope, the user and the timestamp. | FR-10 | Not run
1C-31 | Phase 1C | Phase 1C | File request | P1 | Manual | Building a flow with a requested-file-received trigger. | Save without selecting a named request. | Saving is refused. The trigger is highlighted with a reason that a real named file request must be selected first, and no partial flow is stored. | FR-20 / AC-RUN-01 | Not run
1C-32 | Phase 1C | Phase 1C | File request | P1 | Manual | A Deal with an open file request. | Upload the matching file. | The requirement resolves automatically across focus, history and card status. | FR-20 | Not run
1C-33 | Phase 1C | Phase 1C | Required work | P1 | Manual | A Deal with three outstanding requirements. | Attempt a stage move. | All three listed, Continue disabled, each resolvable inline, original action resumes when empty. | FR-19 / AC-RUN-02 | Not run
1C-34 | Phase 1C | Phase 1C | Required work | P1 | Manual | Ten or more outstanding requirements. | Attempt the blocked action. | Every outstanding item is listed with a scrollable dialog. Nothing is truncated, and the count in the heading matches the number of rows. | A12 | Not run
1C-35 | Phase 1C | Phase 1C | Required work | P1 | Manual | A blocked quote-lifecycle action. | Clear the list. | The exact original operation resumes, not a generic fallback. | FR-19 | Not run
1C-36 | Phase 1C | Phase 1C | Handoff | P2 | Manual | Phase 1C shipped. | Open a recipe as an editable copy. | The live recipe keeps running; the copy is independent and the move is stated as one-way. | FR-04 | Not run

## Regression
QA checklist — Regression
The six rules that must not drift. Each states the earliest release it applies from.
Fill in from Status onwards. Everything to the left describes the test.
ID | Release | Applies from | Area | Pri | Method | Precondition | Steps | Expected result | Traces to | Status | Actual result | Build | Environment | Browser / device | Test data | Evidence link | Defect ID | Waiver approved by | Tester | Date | Notes
REG-01 | Regression | Phase 1A | Locked rule 1 | P1 | Automated | Any release. | Create the first related quote on a Qualified Deal. | The Deal moves to In Progress. | Locked rule 1 | Not run
REG-02 | Regression | Phase 1A | Locked rule 2 | P1 | Automated | Any release. | Accept any one relevant quote. | The Deal becomes Won. Remaining groups change value only. | Locked rule 2 | Not run
REG-03 | Regression | Phase 1A | Locked rule 3 | P1 | Automated | Any release. | Reach a state where no viable quote remains. | Lost is derived. Sales supplies the reason and cannot change the outcome. | Locked rule 3 | Not run
REG-04 | Regression | Phase 1C | Locked rule 4 | P1 | Manual | Authoring exists. | Publish a valid change without testing. | Allowed. Only a real conflict blocks publishing. | Locked rule 4 | Not run
REG-05 | Regression | Phase 2 | Locked rule 5 | P1 | Manual | Custom stages exist. | Place the same custom stage in different lifecycle gaps. | The core block library offered is identical every time. | Locked rule 5 | Not run
REG-06 | Regression | Phase 1A | Locked rule 6 | P1 | Automated | Any release. | Search the action catalogue for approve, send, accept, Won or Lost. | None exists as an action. | Locked rule 6 | Not run

## Non-functional
QA checklist — Non-functional
Concurrency, event ordering, partial failure, performance, permissions, accessibility, browsers, audit and recovery.
Fill in from Status onwards.
ID | Release | Applies from | Area | Pri | Method | Precondition | Steps | Expected result | Traces to | Status | Actual result | Build | Environment | Browser / device | Test data | Evidence link | Defect ID | Waiver approved by | Tester | Date | Notes
NF-01 | All | Phase 1A | Concurrency | P1 | Manual | Two users editing the same Automation. | Both save a draft, then both publish within seconds of each other. | One publish succeeds; the second is refused with a message that the version moved on, and offers to reload. No silent overwrite, and the published version matches one editor's intent exactly. | FR-14 | Not run
NF-02 | All | Phase 1A | Concurrency | P1 | Manual | Two users on the same Deal. | Both accept a different quote in the same alternative group at the same time. | Exactly one acceptance wins. The other is refused with a clear reason, and the Deal has one winner, not two. | AC-DEAL-07 | Not run
NF-03 | All | Phase 1A | Event order | P1 | Automated | A Deal with one quote. | Deliver the quote-sent and quote-accepted events out of order. | The Deal ends in the correct final stage regardless of arrival order, and history records the true sequence of quote events. | FR-16 | Not run
NF-04 | All | Phase 1A | Event order | P1 | Automated | A recipe listening to a quote event. | Deliver the same event twice, ten minutes apart. | The second delivery is recognised as already handled. Nothing is created twice. | FR-21 | Not run
NF-05 | All | Phase 1A | Event order | P2 | Automated | An event delayed by an hour in the queue. | Let it arrive late. | It is processed against the Deal's state at the time of processing, and the delay is visible in the run record. | FR-36 | Not run
NF-06 | All | Phase 1A | Partial failure | P1 | Manual | A recipe with three actions; the second one fails. | Trigger it. | The failure is recorded against the run with the step named. Completed actions are not rolled back silently, and a retry does not repeat the ones that already succeeded. | FR-21 | Not run
NF-07 | All | Phase 1A | Partial failure | P1 | Manual | A recipe that failed. | Open the run history. | The failure, its reason, its timestamp and the affected step are all visible without needing server logs. | FR-21 | Not run
NF-08 | All | Phase 1A | Performance | P2 | Manual | An organisation with several thousand Deals and quotes. | Open the pipeline board and the Deal list. | Both render within an acceptable time and the stage counts are correct. Note the measured time in Actual result. | — | Not run
NF-09 | All | Phase 1A | Performance | P2 | Manual | A Deal carrying a long activity history. | Open the Deal. | The page opens without freezing and the timeline pages or scrolls rather than loading everything at once. | — | Not run
NF-10 | All | Phase 1A | Permissions | P1 | Manual | Roles with and without CRM access. | Sign in as each role and attempt to view and edit Leads, Deals and Automations. | Each role sees and can change only what its permissions allow. A role without access gets a clear refusal, not an empty screen. | FR-38 | Not run
NF-11 | All | Phase 1A | Permissions | P1 | Manual | A user limited to one company. | Attempt to open a Deal from another company by direct URL. | Refused. The record is not rendered and nothing about it leaks in the error. | FR-38 | Not run
NF-12 | All | Phase 1A | Accessibility | P2 | Manual | The required-work dialog open. | Navigate it with the keyboard only. | Focus moves into the dialog, stays trapped inside it, every control is reachable, and Escape closes it returning focus to the trigger. | — | Not run
NF-13 | All | Phase 1A | Accessibility | P2 | Manual | The builder open. | Tab through the whole editing flow. | Every interactive element is reachable and has a visible focus state. | — | Not run
NF-14 | All | Phase 1A | Browsers | P2 | Manual | Supported browser matrix agreed. | Run the Phase 1A smoke set on each supported browser and viewport. | Behaviour and layout are consistent. Record browser and version against each run. | — | Not run
NF-15 | All | Phase 1A | Audit | P1 | Manual | A Deal with a full history. | Export or review the audit trail. | Every stage change, value change and Automation result is present with actor and timestamp. Nothing is missing or reordered. | FR-39 | Not run
NF-16 | All | Phase 1A | Recovery | P1 | Manual | Drafts saved and timed work pending. | Restart the server. | Drafts, pending runs and published versions all survive. Pending work resumes on the version it started with. | FR-40 | Not run

## Test Runs
Test runs
One row per execution cycle. The go / no-go decision belongs here, with who made it.
Run | Release | Build / commit | Environment | Browser / device | Scope | Tester | Start | End | Pass | Fail | Blocked | N/A | Not run | Go / no-go | Decided by | Notes
R-01 | Phase 1A | 1A-rc3 | Staging | Chrome 141 / macOS | Full Phase 1A + applicable Regression | KW | 2026-09-01 | 2026-09-04 | 48 | 3 | 1 | 2 | 0 | No-go | CTO | Two S2 defects open — WQ-1183, WQ-1190
Row 5 is a worked example — overwrite or delete it before the first real run.